**RRT/NWAC 2012 Task Force Basics**

| **Task Force Name** | **Preliminary 6-month Work Products\*** | **Facilitator** |
| --- | --- | --- |
| **Cultural Historic Preservation** | 1) Review current programmatic agreement (PA) with SHPPOs regarding emergency response2) Ensure PA is accurately represented in NWACP3) Clarify how States responding under their own authority meet CHP requirements  | Andy Smith, EPA |
| **Derelict Vessels (ongoing)** | 1) Identify types of vessels of concern2) Definition of a derelict vessel3) Method to identify, fund and prioritize | Randy Clark, CG SCR |
| **Dispersants and In Situ Burn** | 1) Create/Revise Decision Memo2) Create/Revise Decision Checklist | Sean Orr, Ecology |
| **General Community Outreach and Liaison** | 1) Identify (pre-event) outreach goals2) Develop key messages/presentation materials for decision makers and stakeholders in high risk counties3) Recommend next steps for 2013 outreach TF  | CDR Agneta Dahl, CG SPS |
| **GRPs in Response/ Advanced Recovery** | 1) Create tactical guidance for areas between open water response and shoreline areas not covered by GRPs | CDR Mike Schoonover, CG SPS |
| **Places of Refuge (ongoing)** | 1) Approve Places of Refuge matrix2) Create outreach plan3) Create guidance of how it works (memo/matrix)4) Conduct exercise (TTX) | Tim Lupher, CG SPS |
| **Shoreline Cleanup and Assessment Technique** | 1) Classify shoreline types 2) Develop initial pre-approved cleanup strategies for each shoreline type 3) Begin to classify/pre-define shoreline segments | Sean Orr, Ecology |
| **Wildlife Plan Update** | 1) Describe the qualifications, types and numbers of people needed to respond to an oiled wildlife event2) Identify the personnel, equipment,and permitting associated with bird hazing3) General Wildlife Plan Update | Andy Carlson, WA DFWCharlie Herbert, USFWS |

\*Work products may change upon consideration during initial meeting of Task Forces.

**Timeline for Work Product Development:**

December 2011 - Finalize Task Force membership

January 2012 - Hold initial Task Force Meeting and decide on schedule and method for work

February - July 2012 - Task Forces create Work Products

August 1, 2012 - Submit final Work Product to Steering Committee

August 2 - October 31, 2012 - Task Force goes dormant

November 1 - 15, 2012 - Edit work product as needed based on public comment

November 16, 2012 - Task Force disbands

**Options for Task Force Membership:**

|  |  |
| --- | --- |
| Active Task Force Member | These individuals attend meetings, and complete work outside of Task Force Meetings. The bulk of the work of creating the specific area planning task is accomplished by these individuals. |
| Advisory Task Force Member | These individuals follow the progress of the Task Force and provide input, but are not expected to attend meetings, or generate area planning products. These are likely subject matter experts or stakeholders who are too busy with other work to be Active Members. |