**CANUSPAC Annex Update Topics**

Work List for JRT

|  |  |  |  |
| --- | --- | --- | --- |
| **TOPIC AREA/END PRODUCT** | **WHO WILL WORK ON THIS, WHO NEEDS TO BE INVOLVED** | **TARGET COMPLETION DATE** | **CONSTRAINTS/COMMENTS** |
| **JOINT UAC CONCEPT:*** Write-up/Section in CANUSPAC Annex
* Description of JUAC
* Include JRT role/interaction with JUAC and ICPs
* Identify suggested Triggers to go to JUAC
 | * D13
* SPS
* CCG
* D11 IMPA
 | 31OCT2014 |  |
| **International Liaison Officer vs. Agency Rep:*** Write -up/Section modification in CANUSPAC Annex
* Clarify/deconflict with ICS’ LOFR/LNO
* Define some roles/responsibilities
* Reference new IMH/copy that language as appropriate
 | * D13
* SPS
* CCG
* BC MOE
* WA ECY
 | 28NOV2014 |  |
| **Initial Press Release – Adoption and Inclusion in CANUSPAC Annex:*** Review current language as is
* Modify if necessary
* Adopt and include in CANUSPAC Annex
 | * D13
* SPS
* CCG
* BC MOE
* WA ECY
 | 30SEP2014 |  |
| **Gap Analysis for Joint JIC Concept using NWACP JIC Manual:*** Gathering of Comms/PA/JIC specialists from each UC agency on US and CAN sides
* Review NWACP JIC Manual as reference guide to form and run a JOINT Bi-National JIC during a Transboundary response.
* Output: set of recommendations to build into CANSUPAC Annex on development of language/manual for JOINT Bi-National JIC
* Consider updating/creating Media Strategy
* Have them report out at next JRT Meeting
 | Comms/PA Specialists from:* D13
* SPS
* CCG
* BC MOE
* WA ECY
* EC
 | 31JAN2015 |  |
| **CANUSDIX OILED WILDLIFE PLANNING: Identify what we can adopt/include in CANUSPAC Annex*** Identify any elements that can be taken over just as is
* Identify other issues that need to be addressed
* Conference call/webinar to go over the CANUSDIX annex and pull out key points that can be adopted as is, and areas that CANUSPAC needs to include
* Write up that includes all this info
 | * BC MOE
* US DOI
* NOAA
* WA ECY
* WA DFW(?)
* Env Can
* CWS
* DFO
* Other trustees as appropriate
 | 31DEC2014 |  |