**CANUSPAC Annex Update Topics**

Work List for JRT

|  |  |  |  |
| --- | --- | --- | --- |
| **TOPIC AREA/END PRODUCT** | **WHO WILL WORK ON THIS, WHO NEEDS TO BE INVOLVED** | **TARGET COMPLETION DATE** | **CONSTRAINTS/COMMENTS** |
| **JOINT UAC CONCEPT:**   * Write-up/Section in CANUSPAC Annex * Description of JUAC * Include JRT role/interaction with JUAC and ICPs * Identify suggested Triggers to go to JUAC | * D13 * SPS * CCG * D11 IMPA | 31OCT2014 |  |
| **International Liaison Officer vs. Agency Rep:**   * Write -up/Section modification in CANUSPAC Annex * Clarify/deconflict with ICS’ LOFR/LNO * Define some roles/responsibilities * Reference new IMH/copy that language as appropriate | * D13 * SPS * CCG * BC MOE * WA ECY | 28NOV2014 |  |
| **Initial Press Release – Adoption and Inclusion in CANUSPAC Annex:**   * Review current language as is * Modify if necessary * Adopt and include in CANUSPAC Annex | * D13 * SPS * CCG * BC MOE * WA ECY | 30SEP2014 |  |
| **Gap Analysis for Joint JIC Concept using NWACP JIC Manual:**   * Gathering of Comms/PA/JIC specialists from each UC agency on US and CAN sides * Review NWACP JIC Manual as reference guide to form and run a JOINT Bi-National JIC during a Transboundary response. * Output: set of recommendations to build into CANSUPAC Annex on development of language/manual for JOINT Bi-National JIC * Consider updating/creating Media Strategy * Have them report out at next JRT Meeting | Comms/PA Specialists from:   * D13 * SPS * CCG * BC MOE * WA ECY * EC | 31JAN2015 |  |
| **CANUSDIX OILED WILDLIFE PLANNING: Identify what we can adopt/include in CANUSPAC Annex**   * Identify any elements that can be taken over just as is * Identify other issues that need to be addressed * Conference call/webinar to go over the CANUSDIX annex and pull out key points that can be adopted as is, and areas that CANUSPAC needs to include * Write up that includes all this info | * BC MOE * US DOI * NOAA * WA ECY * WA DFW(?) * Env Can * CWS * DFO * Other trustees as appropriate | 31DEC2014 |  |